## Active Clusters
ITDBA-1586 Snapshot Coverage Working Sheet
Goal: confirm every active physical Oracle cluster that needs snapshot protection, including primary clusters and any standby or backup clusters that still need snapshots. Justin confirmed snapshots are usually taken at host/cluster level. If the whole cluster is protected, new storage added later is automatically covered.
Cluster Name / Server | Role | Database / Service | LUNs Info | Storage Array | Snapshot Schedule | Retention | Protection Scope | Current Status | Verified By | Verified Date | Notes / Change Needed
ausdb0a01/02/03 (not 04) | Mixed | Teller / Marketing | All Cluster LUNs + /u01 | aus-admin-Pure4 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | Teller Primary; Marketing Standby DBs
ausdb0b01/02/03 | Mixed | Teller / Marketing | All Cluster LUNs + /u01 | aus-admin-Pure1 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | Teller Standby; Marketing Primary DBs
ausdbdw0b01/02 | Primary |  | All Cluster LUNs + /u01 | aus-admin-Pure2 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | Primary DBs
ausdb0c01/c02 | Primary |  | All Cluster LUNs + /u01 | aus-admin-Pure3 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | Primary DBs
ausdb0d01/d02 | Primary |  | All Cluster LUNs + /u01 | aus-admin-Pure3 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | Primary DBs
ausdb0f01/ausdb0f02 | Primary |  | All Cluster LUNs + /u01 | aus-admin-Pure4 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | Primary DBs
ausdb0e02 | Primary |  | All Cluster LUNs + /u01 | aus-admin-Pure3 | 12:00 AM Every Day | 7 days | Whole cluster | Needs verification |  |  | ausdb0e01 is crossed out in the old page; confirm e02 is still active and on Pure3

## Inactive Retired
Inactive / Retired Snapshot Entries
These rows were crossed out on the old Confluence page. Keep them here for history, but confirm they are no longer needed before removing their snapshots. Justin said that if an entry is no longer needed, remove it from the active list and the storage team can remove the snapshots.
Cluster Name / Server | Previous LUNs Info | Previous Storage Array | Previous Schedule | Previous Retention | Previous Notes | Reason Inactive | Confirmed By | Confirmed Date | Snapshot Removal Status
ausdbedw01/ausdbedw02 | All Cluster LUNs + /u01 | aus-admin-Pure1 | 12:00 AM Every Day | 7 days | Primary DBs and Standby DBs | Crossed out on old Confluence page |  |  | Needs confirmation
testlbedw01/02 | All Cluster LUNs + /u01 | aus-admin-Pure5 | 12:00 AM Every Day | 7 days |  | Crossed out on old Confluence page |  |  | Needs confirmation
ausdb0e01 | [5 empty] | Crossed out beside active ausdb0e02 entry |  |  | Needs confirmation

## Verification Checklist
ITDBA-1586 Verification Checklist
Step | What I need to check | How I will check it | Owner / Person to ask | Status | Evidence / Link | Notes
1 | List every active physical Oracle cluster | Compare the old Confluence page with the current host/cluster list | DBA team | Not started |  | Include primary and any standby/backup cluster that still needs snapshots
2 | Confirm each cluster role | Mark Primary, Standby, Mixed, or Unknown | DBA team | Not started |  | Do not assume from old notes if the setup has changed
3 | Confirm storage array | Check the Pure Storage host/cluster mapping for each cluster | Storage team / Justin | Not started |  | Some clusters may have moved to another Pure array
4 | Confirm snapshot schedule | Check that snapshots run daily at 12:00 AM | Storage team / Justin | Not started |  | Expected schedule is daily at midnight
5 | Confirm retention | Check that retention is still 7 days | Storage team / Justin | Not started |  | Expected retention is 7 days
6 | Confirm protection level | Check whether the whole cluster or only some volumes are protected | Storage team / Justin | Not started |  | Whole-cluster protection is preferred because new storage is covered automatically
7 | Review crossed-out entries | Move retired entries to the inactive sheet and confirm snapshots can be removed | DBA + Storage team | Not started |  | Do not delete history until confirmed
8 | Cross-check for missing clusters | Have another DBA or storage team member review the completed list | Steven / DBA team | Not started |  | No formal approval is required, but a quick peer check is expected
9 | Update Confluence | Replace the old table with Active and Inactive sections | Me | Not started |  | Share the page with the team after publishing

## Confirmed Answers
What I already know from the Jira comments and meeting
Question | Answer I have | Source | Still open?
Should I list primary and standby clusters? | I should list the primary clusters and also any standby or backup clusters that still need snapshots. | Meeting with team and Justin | No
How should I handle crossed-out entries? | I should move them to a separate inactive/retired section or tab, then confirm they are no longer needed. | Meeting | No
What schedule and retention should I expect? | The expected setup is daily at 12:00 AM with 7-day retention, but I still need to verify each cluster. | Meeting | Yes, verify each row
What if storage moved to another Pure array? | I need to update the storage array value to the current one after checking with the storage team. | Meeting | Yes
Do I need proof for every row? | There is no formal proof requirement, but the final list should be cross-checked by another DBA or the storage team. | Meeting | No formal proof
Who approves the final Confluence update? | No formal approval is required. I can publish it, share it with the team, and ask them to check it. | Meeting | No
At what level are snapshots taken? | Snapshots are mostly taken at the host/cluster level. Individual volumes can be used, but whole-cluster protection is preferred. | Justin | No
Why whole-cluster protection? | When new storage is added to a database, it is automatically protected if the whole cluster is covered. | Justin | No